## OVMC
No | Protocol Name | Interface ID (For Bus) | Interface ID (For Tram) | Type | Sender | Receiver | Final Receiver | Plan Date | Finish Date
0 | ST-Connector Coummnication Protocol(message/file)
1 | BUS Main Firmware | FB001 | FT001 | File | DMC | OVMC | OVMC
2 | BUS Sub Firmware | FB002 | FT002 | File | DMC | OVMC | OVMC
3 | BUS Main Voice | FB003 | FT003 | File | DMC | OVMC | OVMC
4 | BUS Sub Voice | FB004 | FT004 | File | DMC | OVMC | OVMC
5 | BUS Route Information | FB500 | FT500 | File | DMC | OVMC | OVMC | 2016-03-08 | 2016-03-08
6 | BUS RouteStop Information | FB501 | FT501 | File | DMC | OVMC | OVMC | 2016-03-08 | 2016-03-08
7 | BUS Operating Parameter Information(Vehicle) | FB502 | FT502 | File | DMC | OVMC | OVMC | 2016-03-08 | 2016-03-08
8 | BUS Driver Information | FB503 | FT503 | File | DMC | OVMC | OVMC | 2016-03-08 | 2016-03-08
9 | BUS Shared BL | FB303 | FT303 | File | DMC | OVMC | OVMC | 2016-03-11 | 2016-03-11
10 | BUS CDC (Changed Data Capture) BL | FB304 | FT304 | File | DMC | OVMC | OVMC | 2016-03-11 | 2016-03-11
11 | System Region Parameter | FB520 | FT520 | File | DMC | OVMC | OVMC | 2016-03-11 | 2016-03-11
12 | Profile Parameter | FB521 | FT521 | File | DMC | OVMC | OVMC | 2016-03-11 | 2016-03-11
13 | Pass Master Parameter | FB522 | FT522 | File | DMC | OVMC | OVMC | 2016-03-15 | 2016-03-15
14 | Stage-set Parameter | FB526 | FT526 | File | DMC | OVMC | OVMC | 2016-03-15 | 2016-03-15
15 | Transit Mode Parameter | FB523 | FT523 | File | DMC | OVMC | OVMC | 2016-03-15 | 2016-03-15
16 | Card Issuer Information | FB525 | FT525 | File | DMC | OVMC | OVMC | 2016-03-18 | 2016-03-18
17 | Time Period Parameter | FB524 | FT524 | File | DMC | OVMC | OVMC | 2016-03-18 | 2016-03-18
18 | Calendar Parameter | FB527 | FT527 | File | DMC | OVMC | OVMC | 2016-03-18 | 2016-03-18
19 | Daylight-Saving Parameter | FB528 | FT528 | File | DMC | OVMC | OVMC | 2016-03-18 | 2016-03-18
20 | Fare Table Parameter | FB529 | FT529 | File | DMC | OVMC | OVMC | 2016-03-22 | 2016-03-22
21 | Discount Profile | FB538 | FT532 | File | DMC | OVMC | OVMC | 2016-03-22 | 2016-03-22
22 | Information of the main equipment installation | MA504 | MA504 | Binary | OVMC | DMC | OASAMC | 2016-03-22 | 2016-03-22
23 | Information of the sub equipment installation | MA507 | MA507 | Binary | OVMC | DMC | OASAMC | 2016-03-22 | 2016-03-22
24 | Version of Equipment | MA505 | MA505 | Binary | OVMC | DMC | OASAMC | 2016-03-22 | 2016-03-22
25 | Transaction Data for boarding and alighting | MA501 | MA501 | Binary | OVMC | DMC | OASAMC | 2016-03-25 | 2016-03-25
26 | Event Information of Equipment | MA503 | MA503 | Binary | OVMC | DMC | OASAMC | 2016-03-25 | 2016-03-25
27 | Request of Equipment Certification | MC401 | MC401 | Binary | OVMC | DMC | OASAMC | 2016-03-25 | 2016-03-25
28 | LGV30 PSAM Card Agency Key-Set for BUS | FB401 | FT401 | File | DMC | OVMC | OVMC | 2016-03-29 | 2016-03-29
29 | LGV30 PSAM Key-Set for BUS | FB402 | FT402 | File | DMC | OVMC | OVMC | 2016-03-29 | 2016-03-29
30 | Response of Equipment Certification | MO402 | MO402 | XML | OVMC | DMC | OASAMC | 2016-03-29 | 2016-03-29
31 | Closing Information of Equipment Transaction Data | MA502 | MA502 | Binary | OVMC | DMC | OASAMC | 2016-03-29 | 2016-03-29

## StandingValidator
No | Protocol Name | Interface ID (For Metro) | Interface ID (For Surburban) | Type | Sender | Receiver | Final Receiver | Plan Date | Finish Date
0 | ST-Connector Coummnication Protocol(message/file)
1 | Request Equipment Data | MM619 | MM619 | Message | SMC | StandingValidator | StandingValidator | 2016-03-08 | 2016-03-08
2 | Cancellation Equipment Data | [6 empty] | 2016-03-08 | 2016-03-08
3 | Request Equipment Log File | [6 empty] | 2016-03-08 | 2016-03-08
4 | Request to Change Equipment Mode | MM620 | MM620 | Message | SMC | StandingValidator | StandingValidator | 2016-03-08 | 2016-03-08
5 | Request Equipment Reset | [6 empty] | 2016-03-08 | 2016-03-08
6 | Request Equipment Boot Mode | [6 empty] | 2016-03-08 | 2016-03-08
7 | Metro Main Firmware | FM031 | FS031 | File | SMC | StandingValidator | StandingValidator
8 | Metro Sub Firmware | FM032 | FS032 | File | SMC | StandingValidator | StandingValidator
9 | Metro Main Voice | FM033 | FS033 | File | SMC | StandingValidator | StandingValidator
10 | Metro Sub Voice | FM034 | FS034 | File | SMC | StandingValidator | StandingValidator
11 | Main Ramdisk Firmware | FM035 | FS035 | File | SMC | StandingValidator | StandingValidator
13 | Main Kernel Firmware | FM036 | FS036 | File | SMC | StandingValidator | StandingValidator
12 | RF Firmware | FM037 | FS037 | File | SMC | StandingValidator | StandingValidator
13 | Metro Shared BL | FM305 | FS305 | File | SMC | StandingValidator | StandingValidator | 2016-03-11 | 2016-03-11
14 | Metro CDC BL | FM306 | FS306 | File | SMC | StandingValidator | StandingValidator | 2016-03-11 | 2016-03-11
17 | Device Own Station | FM614 | FS614 | File | SMC | StandingValidator | StandingValidator | 2016-03-11 | 2016-03-11
18 | Metro Line | FM617 | FS617 | File | SMC | StandingValidator | StandingValidator | 2016-03-11 | 2016-03-11
19 | Metro Station | FM618 | FS618 | File | SMC | StandingValidator | StandingValidator | 2016-03-11 | 2016-03-11
20 | System Region | FM620 | FS620 | File | SMC | StandingValidator | StandingValidator | 2016-03-15 | 2016-03-15
21 | User Profile | FM621 | FS621 | File | SMC | StandingValidator | StandingValidator | 2016-03-15 | 2016-03-15
22 | Pass Master | FM622 | FS622 | File | SMC | StandingValidator | StandingValidator | 2016-03-15 | 2016-03-15
26 | Stage Set | FM626 | FS626 | File | SMC | StandingValidator | StandingValidator | 2016-03-15 | 2016-03-15
23 | Transit Mode | FM623 | FS623 | File | SMC | StandingValidator | StandingValidator | 2016-03-18 | 2016-03-18
24 | Time Period | FM624 | FS624 | File | SMC | StandingValidator | StandingValidator | 2016-03-18 | 2016-03-18
25 | Card Issuer | FM625 | FS625 | File | SMC | StandingValidator | StandingValidator | 2016-03-18 | 2016-03-18
27 | Calendar | FM627 | FS627 | File | SMC | StandingValidator | StandingValidator | 2016-03-18 | 2016-03-18
28 | Daylight-Saving | FM628 | FS628 | File | SMC | StandingValidator | StandingValidator | 2016-03-18 | 2016-03-18
29 | Fare Table | FM629 | FS629 | File | SMC | StandingValidator | StandingValidator | 2016-03-22 | 2016-03-22
30 | Operation Time | FM634 | FS634 | File | SMC | StandingValidator | StandingValidator | 2016-03-22 | 2016-03-22
31 | Transaction Data | MM601 | MM601 | Message | StandingValidator | SMC | OASAMC | 2016-03-22 | 2016-03-22
32 | Closing Data | MM602 | MM602 | Message | StandingValidator | SMC | OASAMC | 2016-03-25 | 2016-03-25
33 | Device Status | MM603 | MM603 | Message | StandingValidator | SMC | OASAMC | 2016-03-25 | 2016-03-25
34 | Alarm/Event | MM604 | MM604 | Message | StandingValidator | SMC | OASAMC | 2016-03-25 | 2016-03-25
35 | Version | MM606 | MM606 | Message | StandingValidator | SMC | OASAMC | 2016-03-25 | 2016-03-25
36 | Sam Id | MM607 | MM607 | Message | StandingValidator | SMC | OASAMC | 2016-03-25 | 2016-03-25
37 | Device H/W Status | MM608 | MM608 | Message | StandingValidator | SMC | OASAMC | 2016-03-29 | 2016-03-29
38 | Device Operation Mode | MM611 | MM611 | Message | StandingValidator | SMC | OASAMC | 2016-03-29 | 2016-03-29
39 | Request All of Operation Files | MM614 | MM614 | Message | StandingValidator | SMC | OASAMC | 2016-03-29 | 2016-03-29
40 | Request an Operation File | MM615 | MM615 | Message | StandingValidator | SMC | OASAMC | 2016-03-29 | 2016-03-29
41 | Request a Version List of Operation Data in Center | MM616 | MM616 | Message | StandingValidator | SMC | OASAMC | 2016-04-01 | 2016-04-01
42 | Request a No. of Last Transaction Data Sequence | MM617 | MM617 | Message | StandingValidator | SMC | OASAMC | 2016-04-01 | 2016-04-01
15 | LGV30 PSAM Card Agency Key Set for Metro | FM401 | FS401 | File | SMC | StandingValidator | StandingValidator | 2016-04-01 | 2016-04-01
16 | LGV30 PSAM Key Set for Metro | FM402 | FS402 | File | SMC | StandingValidator | StandingValidator | 2016-04-01 | 2016-04-01
45 | Send a No. of Last Transaction Data Sequence (Response MM617) | MM618 | MM618 | Message | SMC | StandingValidator | StandingValidator | 2016-04-05 | 2016-04-05
46 | Send Version List of Operation Data in Center (Response MM616) | MM623 | MM623 | Message | SMC | StandingValidator | StandingValidator | 2016-04-05 | 2016-04-05
47 | Send Operation File(s) (Response MM614/MM615) | MM624 | MM624 | Message | SMC | StandingValidator | StandingValidator | 2016-04-05 | 2016-04-05