## Cover
				Athens Project

				Phase 1 Test Report

				SAT-OVM-DDM-01
				Ver. 0.1

				DATE: 22-03-2016

				Prepared By : Süleyman Kabadayı

Copyright © LG CNS
It is forbidden to copy and distribute on certain or whole part of this content without precedent approval of LG CNS

## Document_History
Document History

No	Version	Change Date	Change Cause	Change Description					Author	Approver
1	v.0.1	22.03.2016	new	Initial					Süleyman Kabadayı

## SAT-OVM-DDM-01
▣ Scenario SAT-OVM-DDM-01 :Data Download Management

▶ Desc & Flow
Description		This functionality describes downloading the operational parameter from OVMC to OSCVM.
Biz flow ( It describe briefly )	Communication	OVMC / Connection	Connect / Accept / Response File / Send Version Info / Send Acknowledgement / Send New Parameter List / Request File / Send New Parameters Message			OSCVM / Repeat By File Count

▶ Advance preparation
Preparation		OVMC 1 EA, OSCVM 1 EA

▶ Data
NO	Item	1	2	3		4		5
1	N/A

## 001
Test Case SAT-OVM-DDM-01-001 : Download the pass master (FB522)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the pass master					Written by
Flow		Send version information of pass master / Download the passmaster	Update the passmaster

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of pass master ] / 1.OSCVM sends version information of pass master (or operational parameter)	Test Data A: version file for pass master	Success to send		1st
					2nd
					3rd
2	[Download the passmaster] / 1.OSCVM receives pass master from OVMC		Success to download		1st
					2nd
					3rd
3	[Update the pass master] / 1. OSCVM updates the pass master parameter file	Test Data B: version file for new pass master	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for pass master	FB522.~ (current version)
B	new pass master	FB522.~ (new version)

## 002
Test Case SAT-OVM-DDM-01-002 Download the OSCVM firmware (FB002)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the OSCVM firmware					Written by
Flow		Send version firmware version of the OSCVM firmware / Download the firmware	Update the firmware

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of OSCVM firmware] / 1.OSCVM sends version information of OSCVM firmware	Test Data A : version file for OSCVM firmware	Success to send		1st
					2nd
					3rd
2	[Download the OSCVM firmware] / 1. OSCVM downloads the OSCVM firmware from OVMC (if OVMC sends)	Test Data B : new version file for OSCVM firmware	Success to download		1st
					2nd
					3rd
3	[Update the firmware] 1. OSCVM updates the firmware	Test Data B: version file for firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	the OSCVM firmware	FB002.~ (current version)
B	the new OSCVM firmware	FB002.~ (new version)

## 003
Test Case SAT-OVM-DDM-01-003 :Download the bus route information (FB500)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the bus route information					Written by
Flow		Send version information of bus route / Receive the bus route / Update the bus route

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of bus route] / 1.OSCVM sends version information of bus route	Test Data A: version file for bus route	Success to send		1st
					2nd
					3rd
2	[Receive the bus route] / 1. OSCVM receives the bus route from DMC(if sends OVMC)		Success to receive		1st
					2nd
					3rd
3	[Update the bus route] / 1. OSCVM updates the new bus route	Test Data B: new bus route	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for bus route	FB500.~ (current version)
B	new bus route	FB500.~ (new version)

## 004
Test Case SAT-OVM-DDM-01-004 :Download the bus stop information (FB501 )

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the bus stop of routes					Written by
Flow		Send version information of the bus stop / Receive the bus stop information / Update bus stop information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the bus stop] / 1.OSCVM sends version information of the bus stop	Test Data A: version file for the stop	Success to send		1st
					2nd
					3rd
2	[Receive the bus stop information] / 1.OSCVM receives the bus stop information from DMC(if sends OVMC)		Success to receive		1st
					2nd
					3rd
3	[Update the bus stop information] / 1. OSCVM updates the new bus stop information	Test Data B: new version file for the stop	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for bus route stop	FB501.~ (current version)
B	new version file for bus route stop	FB501.~ (new version)

## 005
Test Case SAT-OVM-DDM-01-005 : Download the bus parameters (FB502)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the bus parameters					Written by
Flow		Send version information of the bus parameters / Download the bus parameters / Update the bus parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the bus parameters] / 1.OSCVM sends version information of the bus parameters	Test Data A: Version file for the bus parameters	Success to send		1st
					2nd
					3rd
2	[Download the bus parameters] / 1. OVMC downloads the bus parameters from DMC(if sends DMC)		Success to download		1st
					2nd
					3rd

3	[Update the bus parameter] 1. OVMC updates the bus parameter file	Test Data B: New bus parameters	Succes to update		1st
					2nd
					3rd

NO	Item
A	Version file for bus parameters	FB502.~ (current version)
B	New bus parameters	FB502.~ (new version)

## 006
Test Case SAT-OVM-DDM-01-006 : Download the bus driver information (FB503)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the bus driver information					Written by
Flow		Send version information of the bus driver information / Download the bus bus driver information / Update the bus driver information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the bus driver information ] / 1.OSCVM sends version information of the bus driver information	Test Data A: Version file for the bus driver information	Success to send		1st
					2nd
					3rd
2	[Download the bus parameters] / 1. OSCVM receives the bus driver information from OVMC (if sends OVMC)		Success to receive		1st
					2nd
					3rd

3	[Update the bus driver information ] 1. OSCVM updates the bus driver information	Test Data B : New bus driver information	Succes to update		1st
					2nd
					3rd

NO	Item
A	Version file for the bus driver information	FB503.~ (current version)
B	New bus driver information	FB503.~ (new version)

## 007
Test Case SAT-OVM-DDM-01-007 : Download the regional parameters (FB520)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the regional parameters					Written by
Flow		Send version information of the regional parameters / Download the regional parameters / Update the regional parameters

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the regional parameters] / 1.OSCVM sends version information of the regional parameters	Test Data A: version file for the regional parameters	Success to send		1st
					2nd
					3rd
2	[Download the regional parameter ] / 1. OSCVM receives the regional parameters from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the regional parameters] 1. OSCVM updates the regional parameters	Test Data B :New Regional Parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	Version file for the regional parameters	FB520.~ (current version)
B	New Regional Parameters	FB520.~ (new version)

## 008
Test Case SAT-OVM-DDM-01-008 : Download LGV30 PSAM Key-Set for BUS (FB402)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the LGV30 PSAM Key-Set for BUS					Written by
Flow		Send version information of the LGV30 PSAM Key-Set for BUS / Download theLGV30 PSAM Key-Set for BUS / Update the LGV30 PSAM Key-Set for BUS

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the LGV30 PSAM Key-Set for BUS] / 1.OSCVM sends version information of the LGV30 PSAM Key-Set for BUS	Test Data A : version file for the LGV30 PSAM Key-Set for BUS	Success to send		1st
					2nd
					3rd
2	[Download theLGV30 PSAM Key-Set for BUS] / 1. OSCVM downloads the LGV30 PSAM Key-Set for BUS from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the LGV30 PSAM Key-Set for BUS] 1. OSCVM updates LGV30 PSAM Key-Set for BUS parameters	Test Data B: new LGV30 PSAM Key-Set for BUS parameters	Succes to update		1st
					2nd
					3rd

NO	Item
A	version file for LGV30 PSAM Key-Set for BUS	FB402.~ (current version)
B	new LGV30 PSAM Key-Set for BUS parameters	FB402.~ (new version)

## 009
Test Case SAT-OVM-DDM-01-009 : Download the transit mode parameters (FB523)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the transit mode parameters					Written by
Flow		Send version information of the transit mode parameters / Download the transit mode parameters / Update transit mode parameters

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the transit mode parameters] / 1.OSCVM sends version information of the transit mode parameters	Test Data A: Version file for the transit mode parameters	Success to send		1st
					2nd
					3rd
2	[Download the transit mode parameters] / 1. OVMC downloads the transit mode parameters from DMC(if sends DMC)		Success to download		1st
					2nd
					3rd
3	[Update transit mode parameters] 1. OVMC updates the transit mode parameters	Test Data B:New transit mode parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	Version file for the transit mode parameters	FB523.~ (current version)
B	New transit mode parameters	FB523.~ (new version)

## 010
Test Case SAT-OMC-OVM-01-010 : Download the time period (FB524)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the time period					Written by
Flow		Send version information of the time period / Download the time period	Update the time period

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the time period] / 1.OSCVM sends version information of the time period	Test Data A: version file for the time period	Success to send		1st
					2nd
					3rd
2	[Download the time period] / 1. OSCVM downloads the time period from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the time period] 1. OSCVM updates the time period parameters	Test Data B:New time period parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the time period	FB524.~ (current version)
B	New transit mode parameters	FB524.~ (new version)

## 011
Test Case SAT-OVM-DDM-01-011 : Download the card issuer ID (FB525)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the card issuer ID					Written by
Flow		Send version information of the card issuer ID / Download the card issuer ID / Update the card issuer ID

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the card issuer ID] / 1.OSCVM sends version information of the card issuer ID	Test Data A: Version file for the card issuer ID	Success to send		1st
					2nd
					3rd
2	[Download the card issuer ID] / 1. OSCVM downloads the card issuer ID from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the time period] 1. OSCVM updates the card issuer ID	Test Data B: New card issuer ID	Succes to update		1st
					2nd
					3rd

NO	Item
A	Version file for the card issuer ID	FB525.~ (current version)
B	New card issuer ID	FB525.~ (new version)

## 012
Test Case SAT-OVM-DDM-01-012 : Download the stage set (FB526)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the stage set					Written by
Flow		Send version information of the stage set / Download the stage set / Update the stage set

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the stage set] / 1.OSCVM sends version information of the stage set	Test Data A: version file for the stage set	Success to send the stage set version		1st
					2nd
					3rd
2	[Download the stage set] / 1. OSCVM downloads the stage set from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the stage set] 1. OSCVM updates stage set	Test Data B: new stage set parameters	Succes to update		1st
					2nd
					3rd

NO	Item
A	version file for the stage set	FB526.~ (current version)
B	new stage set parameters	FB526.~ (new version)

## 013
Test Case SAT-OVM-DDM-01-013 : Download the calendar (FB527)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the calendar					Written by
Flow		Send version information of the calendar / Download the calendar / Update the calendar

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the calendar] / 1.OSCVM sends version information of the calendar	Test Data A: version file for the calendar	Success to send		1st
					2nd
					3rd
2	[Download the calendar] / 1. OSCVM downloads the calendar from OVMC(if sends DMC)		Success to download		1st
					2nd
					3rd
3	[Update the calendar] 1. OSCVM updates calendar	Test Data B: new calendar parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the calendar	FB527.~ (current version)
B	new calendar parameters	FB527.~ (new version)

## 014
Test Case SAT-OVM-DDM-01-014 : Download the daylight saving (FB528)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the daylight saving					Written by
Flow		Send version information of the daylight saving / Download the daylight saving / Update the daylight saving

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the daylight saving] / 1.OSCVM sends version information of the daylight saving	Test Data A: Version file for the daylight saving	Success to send		1st
					2nd
					3rd
2	[Download the daylight saving] / 1.OSCVM downloads the daylight saving from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the daylight saving] 1. OSCVM updates daylight saving	Test Data B : New daylight saving parameters	Succes to update		1st
					2nd
					3rd

NO	Item
A	Version file for the daylight saving	FB528.~ (current version)
B	New daylight saving parameters	FB528.~ (new version)

## 015
Test Case SAT-OVM-DDM-01-015 : Download the shared blacklist (FB303)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the shared blacklist					Written by
Flow		Send version information of the shared blacklist / Download the shared blacklist / Update the shared blacklist

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the shared blacklist] / 1.OSCVM sends version information of the shared blacklist	Test Data A: version file for the shared blacklist	Success to send		1st
					2nd
					3rd
2	[Download the shared blacklist] / 1. OSCVM downloads the shared blacklist from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the shared blacklist] 1. OSCVM updates shared blacklist	Test Data B: new shared blacklist	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the shared blacklist	FB303.~ (current version)
B	new shared blacklist	FB303.~ (new version)

## 016
Test Case SAT-OVM-DDM-01-016: Download the hot blacklist (FB304)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the hot blacklist					Written by
Flow		Send version informationof the hot blacklist / Download the hot blacklist / Update the shared hot blacklist

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version informationof the hot blacklist] / 1.OSCVM sends version information of the hot blacklist	Test Data A: version file for the hot blacklist	Success to send the hot blacklist version		1st
					2nd
					3rd
2	[Download the hot blacklist] / 1. OSCVM downloads the hot blacklist from OVMC(if sends OVMC)		Success to download		1st
					2nd
					3rd
3	[Update the shared hot blacklist] 1. OSCVM updates shared hot blacklist	Test Data B: new shared hot blacklist	Succes to update		1st
					2nd
					3rd

NO	Item
A	version file for the hot blacklist	FB304.~ (current version)
B	new shared hot blacklist	FB304.~ (new version)

## 017
Test Case SAT-OVM-DDM-01-017 : Download the Card/SAM parameters (FB401)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Card/SAM parameters					Written by
Flow		Send version of the Card/SAM parameters / Download the Card/SAM parameters / Update the shared Card/SAM parameters

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the Card/SAM parameters] / 1.OSCVM sends version information of the Card/SAM parameters	Test Data A: version file for the Card/SAM parameters	Success to send		1st
					2nd
					3rd
2	[Download the Card/SAM parameters] / 1.OSCVM downloads the Card/SAM parameters from OVMC		Success to download		1st
					2nd
					3rd
3	[Update the shared Card/SAM parameters] 1. OSCVM updates Card/SAM parameters	Test Data B: new Card/SAM parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Card/SAM parameters	FB401.~ (current version)
B	new shared Card/SAM parameters	FB401.~ (new version)

## 018
Test Case SAT-OVM-DDM-01-018 : Download the sub voice (FB004)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the voice					Written by
Flow		Send version information of the sub voice / Download the voice	Update Sub Voice

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the sub voice] / 1.OSCVM sends version information of the sub voice	Test Data: Version file for the sub voice	Success to send		1st
					2nd
					3rd
2	[Download the voice] / 1. OSCVM downloads the sub voice from OVMC (if sends OVMC)	Test DataB: New version file for the sub voice	Success to download		1st
					2nd
					3rd
3	[Update Update Sub Voice] 1. OSCVM updates Sub Voice	Test Data B: New Sub Voice	Success to update		1st
					2nd
					3rd

NO	Item
A	version information of the sub voice	FB004.~ (current version)
B	new version information of the sub voice	FB004.~ (new version)

## 019
Test Case SAT-OVM-DDM-01-019 : Download the discount profile (FB538)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the discount profile					Written by
Flow		Send version of the discount profile / Download the discount profile / Update the shared discount profile

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the discount profile] / 1.OSCVM sends version information of the discount profile	Test Data A: Version file for the discount profile	Success to send the discount profile version		1st
					2nd
					3rd
2	[Download the discount profile] / 1. OSCVM downloads the discount profile from OVMC		Success to download		1st
					2nd
					3rd
3	[Update the shared discount profile] 1.OSCVM updates discount profile	Test Data B: New discount profile	Success to update		1st
					2nd
					3rd

NO	Item
A	Version file for the discount profile	FB538.~ (current version)
B	New shared discount profile	FB538.~ (new version)