## Cover
				Athens Project

				Phase 1 Test Report

				SAT-CVM-DDM-01
				Ver. 0.1

				DATE: 22-03-2016

				Prepared By : Süleyman Kabadayı

Copyright © LG CNS
It is forbidden to copy and distribute on certain or whole part of this content without precedent approval of LG CNS

## Document_History
Document History

No	Version	Change Date	Change Cause	Change Description					Author	Approver
1	v.0.1	22.03.2016	new	Initial					Süleyman Kabadayı

## SAT-CVM-DDM-01
▣ Scenario SAT-CVM-DDM-01 :Data Download Management

▶ Desc & Flow
Description		To provide the functions of downloading and updating.SCVM, and the downloaded data is stored in a different download folder. After checking the file updating conditions, SCVM starts the update process. / SCVM receive Firmware (SCVM), Voice file,Operational parameter,Fare Table,Blacklist, Calendar date,Time, Line/Station information
Biz flow ( It describe briefly )	Communication	Connection / SCVM	Send Version Info / Connect / Accept / Request File / Send Acknowledgement / Response File / Send Version Info / Send New Parameter List			Repeat By File Count / SMC		Check Version

▶ Advance preparation
Preparation		SCVM 1 EA, SMC 1 EA

▶ Data
NO	Item	1	2	3		4		5
1	N/A

## 001
Test Case SAT-CVM-DDM-01-001 : Download RAIL Main FirmwareFS(FM)031

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Main Firmware					Written by
Flow		Send version information of RAIL Main Firmware / Download RAIL Main Firmware	Update RAIL Main Firmware

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of RAIL Main Firmware ] / 1.SCVM sends version information of RAIL Main Firmware	Test Data A: version file for RAIL Main Firmware	Success to send		1st
					2nd
					3rd
2	[Download the RAIL Main Firmware] / 1.SCVM downloads RAIL Main Firmware (if SMC sends)		Success to download		1st
					2nd
					3rd
3	[Update the RAIL Main Firmware] / 1. SCVM updates RAIL Main Firmware file	Test Data B: new RAIL Main Firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for RAIL Main Firmware	FS(FM)031.~ (current version)
B	new RAIL Main Firmware	FS(FM)031.~ (new version)

## 002
Test Case SAT-CVM-DDM-01-002 : Download RAIL Sub Firmware FS(FM)032

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Sub Firmware					Written by
Flow		Send version firmware version of the RAIL Sub Firmware / Download the firmware	Update the firmware

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version firmware version of the RAIL Sub Firmware] / 1.SCVM sends version information of the firmware (or operational parameter)	Test Data A: version file for the firmware	Success to send		1st
					2nd
					3rd
2	[Download the firmware] / 1.SCVM downloads the firmware from DMC (if DMC sends)		Success to download		1st
					2nd
					3rd
3	[Update the RAIL Main Firmware] / 1.SCVM updates RAIL Sub Firmware file	Test Data B: New RAIL Sub Firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the firmware	FS(FM)032.~ (current version)
B	New RAIL Sub firmware	FS(FM)032.~ (new version)

## 003
Test Case SAT-CVM-DDM-01-003 Download RAIL Main Voice FS(FM)033

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Main Voice					Written by
Flow		Send information version of RAIL Main Voice / Download the RAIL Main Voice	Download the RAIL Main Voice

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send information version of RAIL Main Voice ] / 1.SCVM sends version information of SCVM firmware	Test Data A : version file for RAIL Main Voice	Success to send		1st
					2nd
					3rd
2	[Download the RAIL Main Voice ] / 1. OVMC downloads the RAIL Main Voice / from SMC(if SMC sends)		Success to download		1st
					2nd
					3rd
3	[Update the RAIL Main Voice ] / 1. SCVM updates RAIL Main Voice	Test Data B: new RAIL Main Voice	Success to update		1st
					2nd
					3rd

NO	Item
A	the RAIL Main Voice	FS(FM)033.~ (current version)
B	new RAIL Main Voice	FS(FM)033.~ (new version)

## 004
Test Case SAT-CVM-DDM-01-004 :Download RAIL Sub Voice FS(FM)034

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Sub Voice					Written by
Flow		Send version information of RAIL Sub Voice / Receive the RAIL Sub Voice

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of RAIL Sub Voice] / 1.SCVM sends version information of bus route	Test Data A: version file for RAIL Sub Voice	Success to send		1st
					2nd
					3rd
2	[Receive the RAIL Sub Voice] / 1. SCVM downloads the bus route from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the RAIL Main Voice ] / 1. SCVM updates RAIL Sub Voice	Test Data B:new RAIL Sub Voice	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for RAIL Sub Voice	FS(FM)034.~ (current version)
B	new RAIL Sub Voice	FS(FM)034.~ (new version)

## 005
Test Case SAT-CVM-DDM-01-005 ::Download Main Ramdisk Firmware FS(FM)035

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		:Download Main Ramdisk Firmware					Written by
Flow		Send version information of Main Ramdisk Firmware / Receive the Main Ramdisk Firmware information / Update the Main Ramdisk Firmware information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of Main Ramdisk Firmware ] / 1.SCVM sends version information of Main Ramdisk Firmware	Test Data A: version file for Main Ramdisk Firmware	Success to send		1st
					2nd
					3rd
2	[Receive the Main Ramdisk Firmware / information] / 1. SCVM receives the Main Ramdisk Firmware / from SMC(if sends SMC)		Success to receive		1st
					2nd
					3rd
3	[Update the Main Ramdisk Firmware information] / 1. SCVM updates the Main Ramdisk Firmware	Test Data B: new version file for Main Ramdisk Firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for Main Ramdisk Firmware	FS(FM)035.~ (current version)
B	new version file for Main Ramdisk Firmware	FS(FM)035.~ (new version)

## 006
Test Case SAT-CVM-DDM-01-006 :Main Kernel Firmware FS(FM)036

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Main Kernel Firmware					Written by
Flow		Send version information of the Main Kernel Firmware / Download Main Kernel Firmware / Update the Main Kernel Firmware

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the Main Kernel Firmware] / 1.SCVM sends version information of the Main Kernel Firmware	Test Data A: version file for the Main Kernel Firmware	Success to send		1st
					2nd
					3rd
2	[Download the Main Kernel Firmware] / 1.SCVM downloads the Main Kernel Firmware from SMC (if sends SMC)		Success to download		1st
					2nd
					3rd

3	[Update the bus parameter] 1. SCVM updates the Main Kernel Firmware file	Test Data B: new Main Kernel Firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for Main Kernel Firmware	FS(FM)036.~ (current version)
B	new Main Kernel Firmware	FS(FM)036.~ (new version)

## 007
Test Case SAT-CVM-01-007 : Download RF Firmware FS(FM)037

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RF Firmware					Written by
Flow		Send version information of the RF Firmware / Download the RF Firmware / Update the RF Firmware

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the RF Firmware information ] / 1.SCVM sends version information of the RF Firmware	Test Data A: version file for the RF Firmware information	Success to send		1st
					2nd
					3rd
2	[Download the RF Firmware] / 1.SCVM downloads the RF Firmware information from SMC (if sends SMC)		Success to download		1st
					2nd
					3rd

3	[Update the RF Firmware information ] 1. SCVM updates the RF Firmware file	Test Data B : new RF Firmware	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the RF Firmware information	FS(FM)037.~ (current version)
B	new RF Firmware	FS(FM)037.~ (new version)

## 008
Test Case SAT-CVM-DDM-01-008 : Download RAIL Fixed BL FS(FM)305

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Fixed BL					Written by
Flow		Send version information of the RAIL Fixed BL / Download RAIL Fixed BL / Update the RAIL Fixed BL

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the RAIL Fixed BL ] / 1.SCVM sends version information of the RAIL Fixed BL	Test Data A: version file for the RAIL Fixed BL	Success to send		1st
					2nd
					3rd
2	[Download the RAIL Fixed BL ] / 1.SCVM downloads the RAIL Fixed BL from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the RAIL Fixed BL ] 1. SCVM updates the RAIL Fixed BL	Test Data B :New RAIL Fixed BL	Success to Update		1st
					2nd
					3rd

NO	Item
A	Version file for the RAIL Fixed BL	FS(FM)305.~ (current version)
B	New RAIL Fixed BL	FS(FM)305.~ (new version)

## 009
Test Case SAT-CVM-DDM-01-009 : Download LGV30 PSAM Key-Set for BUS (FB402)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download LGV30 PSAM Key-Set for BUS					Written by
Flow		Send version information of the LGV30 PSAM Key-Set for BUS / Download the LGV30 PSAM Key-Set for BUS	Update the LGV30 PSAM Key-Set for BUS

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the LGV30 PSAM Key-Set for BUS] / 1.SCVM sends version information of the LGV30 PSAM Key-Set for BUS	Test Data A : version file for the LGV30 PSAM Key-Set for BUS	Success to send		1st
					2nd
					3rd
2	[Download the LGV30 PSAM Key-Set for BUS] / 1. SCVM downloads the LGV30 PSAM Key-Set for BUS from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the LGV30 PSAM Key-Set for BUS] 1. SCVM updates LGV30 PSAM Key-Set for BUS	Test Data B: new LGV30 PSAM Key-Set for BUS parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for LGV30 PSAM Key-Set for BUS	FB402.~ (current version)
B	new LGV30 PSAM Key-Set for BUS parameters	FB402.~ (new version)

## 010
Test Case SAT-CVM-DDM-01-010 : Download RAIL Variable BL FS(FM)306

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Variable BL					Written by
Flow		Send version information of the RAIL Variable BL / Download the RAIL Variable BL / Update RAIL Variable BL

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of th RAIL Variable BL ] / 1.SCVM sends version information of RAIL Variable BL	Test Data A: version file for the RAIL Variable BL	Success to send		1st
					2nd
					3rd
2	[Download theRAIL Variable BL ] / 1. SCVM downloads the RAIL Variable BL from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update RAIL Variable BL ] 1. SCVM updates the RAIL Variable BL	Test Data B:New RAIL Variable BL	Success to Update		1st
					2nd
					3rd

NO	Item
A	version file for the RAIL Variable BL	FS(FM)306.~ (current version)
B	New RAIL Variable BL	FS(FM)306.~ (new version)

## 011
Test Case SAT-CVM-DDM-01-011 :Download LGV30 PSAM Card Agency KeySet for RAIL FS(FM)401

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download LGV30 PSAM Card Agency KeySet for RAIL FS					Written by
Flow		Send version information of the LGV30 PSAM Card Agency KeySet for RAIL FS / Download the LGV30 PSAM Card Agency KeySet for RAIL FS	Update LGV30 PSAM Card Agency KeySet for RAIL FS

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the LGV30 PSAM Card Agency KeySet for RAIL FS] / 1.SCVM sends version information of the LGV30 PSAM Card Agency KeySet for RAIL FS	Test Data A: version file for the LGV30 PSAM Card Agency KeySet for RAILFS	Success to send		1st
					2nd
					3rd
2	[Download the LGV30 PSAM Card Agency KeySet for RAIL FS] / 1.SCVM downloads the LGV30 PSAM Card Agency KeySet for RAIL FS from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the LGV30 PSAM Card Agency KeySet for RAIL FS ] 1.SCVM updates the LGV30 PSAM Card Agency KeySet for RAIL FS	Test Data B:New time LGV30 PSAM Card Agency KeySet for RAIL FS	Success to Update		1st
					2nd
					3rd

NO	Item
A	Version file for the LGV30 PSAM Card Agency KeySet for RAIL FS	FS(FM)401.~ (current version)
B	New LGV30 PSAM Card Agency KeySet for RAIL FS	FS(FM)401.~ (new version)

## 012
Test Case SAT-CVM-DDM-01-012 : Download LGV30 PSAM KeySet for RAIL FS(FM)402

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download LGV30 PSAM KeySet for RAIL FS(FM)402					Written by
Flow		Send version information of the LGV30 PSAM KeySet for RAIL / Download the LGV30 PSAM KeySet for RAIL / Update the LGV30 PSAM KeySet for RAIL

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the LGV30 PSAM KeySet for RAIL] / 1.SCVM sends version information of LGV30 PSAM KeySet for RAIL	Test Data A: version file for the LGV30 PSAM KeySet for RAIL	Success to send		1st
					2nd
					3rd
2	[Download the LGV30 PSAM KeySet for RAIL] / 1. SCVM downloads the LGV30 PSAM KeySet for RAIL from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the LGV30 PSAM KeySet for RAIL] 1. SCVM updates new LGV30 PSAM KeySet for RAIL	Test Data B: new LGV30 PSAM KeySet for RAIL	Success to Update		1st
					2nd
					3rd

NO	Item
A	version file for the LGV30 PSAM KeySet for RAIL	FS(FM)402.~ (current version)
B	new LGV30 PSAM KeySet for RAIL	FS(FM)402.~ (new version)

## 013
Test Case SAT-CVM-DDM-01-013 : Download Device Own Station FS(FM)614

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download Device Own Station					Written by
Flow		Send version information of the Device Own Station / Receive the Device Own Station / Update the Device Own Station

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of theDevice Own Station] / 1.SCVM sends version information of the Device Own Station	Test Data A: version file for the Device Own Station	Success to send the Device Own Station version		1st
					2nd
					3rd
2	[Download the Device Own Station] / 1. SCVM receives the Device Own Station from SMC(if sends SMC)		Success to receive		1st
					2nd
					3rd
3	[Update the Device Own Station] 1. SCVM updates Device Own Station	Test Data B: new stage Device Own Station	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Device Own Station	FS(FM)614.~ (current version)
B	new Device Own Station	FS(FM)614.~ (new version)

## 014
Test Case SAT-CVM-DDM-01-014 : Download RAIL Line Information FS(FM)617

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Line Information					Written by
Flow		Send version information of the RAIL Line / Receive the RAIL Line Information / Update the RAIL Line Information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the RAIL Line ] / 1.SCVM sends version information of the RAIL Line	Test Data A: version file for the RAIL Line information	Success to send		1st
					2nd
					3rd
2	[Download the RAIL Line Information / ] / 1. SCVM receives the RAIL Line information from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the the RAIL information] 1. SCVM updates RAIL Line information	Test Data B: new the RAIL information	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the RAIL Line information	FS(FM)617.~ (current version)
B	new the RAIL information	FS(FM)617.~ (new version)

## 015
Test Case SAT-CVM-DDM-01-015 : Download RAIL Station Information FS(FM)618

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download RAIL Station Information					Written by
Flow		Send version information of RAIL Station / Receive the RAIL Station Information / Update the RAIL Station Information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the RAIL Station] / 1.SCVM sends version information of the RAIL Station	Test Data A: version file for the RAIL Station Information	Success to send		1st
					2nd
					3rd
2	[Download the shared blacklist] / 1. SCVM receives the RAIL Station Information from SMC(if sends SMC)		Success to receive		1st
					2nd
					3rd
3	[Update the shared blacklist] 1. SCVM updates the RAIL Station Information	Test Data B: new the RAIL Station Information	Success to receive		1st
					2nd
					3rd

NO	Item
A	version file for the the RAIL Station Information	FS(FM)618.~ (current version)
B	new the RAIL Station Information	FS(FM)618.~ (new version)

## 016
Test Case SAT-CVM-DDM-01-016: Download System Region Parameter FS(FM)620

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the System Region Parameter					Written by
Flow		Send version information of the System Region Parameter / Download the System Region Parameter / Update the System Region Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version informationof the System Region Parameter] / 1.SCVM sends version information of the System Region Parameter	Test Data A: version file for the System Region Parameter	Success to send		1st
					2nd
					3rd
2	[Download the System Region Parameter] / 1. SCVM downloads the System Region Parameter from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the System Region Parameter] 1. SCVM updates System Region Parameter	Test Data B: new System Region Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the System Region Parameter	FS(FM)620.~ (current version)
B	new System Region Parameter	FS(FM)620.~ (new version)

## 017
Test Case SAT-CVM-DDM-01-017 : Download the Download Profile Parameter FS(FM)621

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Profile Parameters					Written by
Flow		Send version of the Profile Parameters / Download the Profile Parameters / Update the Profile Parameters

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the Profile Parameters] / 1.SCVM sends version information of the Profile Parameters	Test Data A: version file for the Profile Parameters	Success to send		1st
					2nd
					3rd
2	[Download the Profile Parameters] / 1.SCVM downloads the Profile Parameters from SMC		Success to download		1st
					2nd
					3rd
3	[Update the Profile Parameters] 1. OVMC updates Profile Parameters	Test Data B: new Profile Parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Profile Parameters	FS(FM)621.~ (current version)
B	new Profile Parameters	FS(FM)621.~ (new version)

## 018
Test Case SAT-CVM-DDM-01-018 : Download Pass Master Parameter FS(FM)622

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Pass Master Parameter					Written by
Flow		Send version information of the Pass Master Parameter / Download the Pass Master Parameter / Update the Pass Master Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the Pass Master Parameter] / 1.SCVM sends version information of the Pass Master Parameter	Test Data A: version file for the Pass Master Parameter	Success to send		1st
					2nd
					3rd
2	[Download the Pass Master Parameter] / 1.SCVM downloads thePass Master Parameter from SMC (if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the Pass Master Parameter] 1.SCVM updates Pass Master Parameter	Test Data B: new Pass Master Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version information of the Pass Master Parameter	FS(FM)622.~ (current version)
B	new version information of the Pass Master Parameter	FS(FM)622.~ (new version)

## 019
Test Case SAT-CVM-DDM-01-019 : Download TrafficMeans Parameter FS(FM)623

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download TrafficMeans Parameter					Written by
Flow		Send version information of the TrafficMeans Parameter / Download the TrafficMeans Parameter	Update the TrafficMeans Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the TrafficMeans Parameter] / 1.SCVM sends version information of the TrafficMeans Parameter	Test Data: version file for the TrafficMeans Parameter	Success to send		1st
					2nd
					3rd
2	[Download the TrafficMeans Parameter] / 1. SCVM downloads the TrafficMeans Parameter from SMC (if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the TrafficMeans Parameter] 1.SCVM updates the TrafficMeans Parameter	Test DataB: new version file for the TrafficMeans Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version information of the TrafficMeans Parameter	FS(FM)623.~ (current version)
B	new version information of the TrafficMeans Parameter	FS(FM)623.~ (new version)

## 020
Test Case SAT-CVM-DDM-01-020 : Download Time Period Parameter FS(FM)624

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Time Period Parameter					Written by
Flow		Send version of the Time Period Parameter / Download the Time Period Parameter / Update the Time Period Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the Time Period Parameter] / 1.SCVM sends version information of the Time Period Parameter	Test Data A: version file for the Time Period Parameter	Success to send		1st
					2nd
					3rd
2	[Download the Time Period Parameter] / 1. SCVM downloads the Time Period Parameter from SMC		Success to download		1st
					2nd
					3rd
3	[Update the Time Period Parameter] 1. OVMC updates Time Period Parameter	Test Data B: new Time Period Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Time Period Parameter	FS(FM)624.~ (current version)
B	new Time Period Parameter	FS(FM)624.~ (new version)

## 021
Test Case SAT-CVM-DDM-01-021 : Download Issuer Information FS(FM)625

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Issuer Information					Written by
Flow		Send version of the Issuer Information / Download the Issuer Information / Update the Issuer Information

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of thediscount profile] / 1.SCVM sends version information of the Issuer Information	Test Data A: version file for the Issuer Information	Success to send		1st
					2nd
					3rd
2	[Download the Issuer Information] / 1. SCVM downloads the Time Period Parameter from SMC		Success to download		1st
					2nd
					3rd
3	[Update the Issuer Information] 1. SCVM updates Issuer Information	Test Data B: new Issuer Information	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Issuer Information	FS(FM)625.~ (current version)
B	new Issuer Information	FS(FM)625.~ (new version)

## 022
Test Case SAT-CVM-DDM-01-022 :Download Stage-set Parameter FS(FM)626

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download Stage-set Parameter					Written by
Flow		Send version of the Stage-set Parameter / Download the Stage-set Parameter / Update the Stage-set Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the Stage-set Parameter] / 1.SCVM sends version information of the Stage-set Parameter	Test Data A: version file for the Stage-set Parameter	Success to send		1st
					2nd
					3rd
2	[Download the Stage-set Parameter] / 1.SCVM downloads the Stage-set Parameter from SMC		Success to download		1st
					2nd
					3rd
3	[Update the Stage-set Parameter] 1. SCVM updates Stage-set Parameter	Test Data B: new Stage-set Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Stage-set Parameter	FS(FM)626.~ (current version)
B	new Stage-set Parameter	FS(FM)626.~ (new version)

## 023
Test Case SAT-CVM-DDM-01-023:Download Calendar Parameter FS(FM)627

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the Calendar Parameter					Written by
Flow		Send version of the Calendar Parameter / Download the Calendar Parameter / Update the Calendar Parameter

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of the Calendar Parameter] / 1.SCVM sends version information of the Calendar Parameter	Test Data A: version file for the Calendar Parameter	Success to send		1st
					2nd
					3rd
2	[Download the Calendar Parameter] / 1.SCVM downloads the Calendar Parameter from SMC		Success to download		1st
					2nd
					3rd
3	[Update the Calendar Parameter] 1. SCVM updates Calendar Parameter	Test Data B: new Calendar Parameter	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the Calendar Parameter	FS(FM)627.~ (current version)
B	new Calendar Parameter	FS(FM)627.~ (new version)

## 024
Test Case SAT-CVM-01-024 : Download the daylight saving FS(FM628)

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the daylight saving					Written by
Flow		Send version information of the daylight saving parameters / Download the daylight saving parameters / Update the daylight saving parameters

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version information of the daylight saving parameters] / 1.SCVM send version information of the daylight saving parameters	Test Data A: version file for the daylight saving parameters	Success to send		1st
					2nd
					3rd
2	[Download the daylight saving] / 1. SCVM downloads the daylight saving parameters from SMC(if sends SMC)		Success to download		1st
					2nd
					3rd
3	[Update the daylight saving parameters] 1. SCVM updates daylight saving parameters	Test Data B : new daylight saving parameters	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the daylight saving parameters	FS(FM)628.~ (current version)
B	new daylight saving parameters	FS(FM)628.~ (new version)

## 025
Test Case SAT-CVM-DDM-01-025 : Download Discount Profile FS(FM)538

1. Test Scenario
Test date		1st		Tester		1st
		2nd				2nd
		3rd				3rd

Description		Download the discount profile					Written by
Flow		Send version of the discount profile / Download the discount profile / Update the discount profile

NO	Task	Test data	Expected result	Person in charge	Result		Pass/Fail			Remark
					1st	2nd	3rd
1	[Send version of thediscount profile] / 1.SCVM sends version information of the discount profile	Test Data A: version file for the discount profile	Success to send		1st
					2nd
					3rd
2	[Download the discount profile] / 1. SCVM downloads the discount profile from SMC		Success to download		1st
					2nd
					3rd
3	[Update the shared discount profile] 1. SCVM updates discount profile	Test Data B: new discount profile	Success to update		1st
					2nd
					3rd

NO	Item
A	version file for the discount profile	FS(FM)538.~ (current version)
B	new shared discount profile	FS(FM)538.~ (new version)