## Cover
Athens e-Ticketing System
Phase 1 Test Report
SIT-OVM-MAO-04
Ver. 1.0
DATE: 10-02-2016
Prepared By : Application Team
Copyright © LG CNS
It is forbidden to copy and distribute on certain or whole part of this content without precedent approval of LG CNS

## Document History
Document History
No | Version | Change Date | Change Cause | Change Description | Author | Approver
1 | v1.0 | 10-02-2016 | new | Initial | Application Team | K.H.Ryu
업무기능분해도
국민대학교 종합정보시스템 구축

## SIT-OVM-DUM-04
▣ Scenario SIT-OVM-DUM-04
▶ Desc & Flow
Description |  | Device status information upload from OSCVM/OVMC to DMC
Biz flow
▶ Advance preparation
Preparation |  | OSCVM, OVMC, DMC, AMC, OASA-MC 1ea
▶ Data
NO | Item | 1 | 2 | 3 | 4 | 5
1 | N/A
OVMC,OSCVM
002. Upload status data to AMC
001. Send status data to DMC
DMC
AMC
AMC
OASA-MC
003. Transmit status data to OASA-MC
004. Receive status data at OASA-MC

## 001
▶ Test Case SIT-OVM-DUM-04-001 : Device status information upload from OSCVM/OVMC to DMC
1. Test Scenario
Test date |  | 1st |  | Tester |  | 1st
|  | 2nd |  |  |  | 2nd
|  | 3rd |  |  |  | 3rd
Description |  | Device status information upload from OSCVM/OVMC to DMC |  |  |  |  | Written by |  | KIM J.E.
Flow
NO | Task | Test data | Expected result | Person in charge | Result |  | Pass/Fail |  |  | Remark
[7 empty] | 1st | 2nd | 3rd
1 | OSCVM save and send the status data to OVMC. OVMC save the status data | Test data : A | Send / Save Ok | KIM J.E. | 1st |  |  |  |  | Test Data:B
2nd
3rd
2 | Upload the status data to DMC | Test data : A | Upload OK | KIM J.E. | 1st |  |  |  |  | Test Data:B
2nd
3rd
2. Test Data
NO | Item | Value
A | Event Information of Equipment (MA503) | Status (Event) Code : DeActivated
B
OSCVM save and send the status data to OVMC. OVMC save the status data
Upload the status data to DMC

## 002
▶ Test Case SIT-OVM-DUM-04-002 : Receiving device status information / sending from DMC to AMC
1. Test Scenario
Test date |  | 1st |  | Tester |  | 1st
|  | 2nd |  |  |  | 2nd
|  | 3rd |  |  |  | 3rd
Description |  | Receiving device status information / sending from DMC to AMC |  |  |  |  | Written by |  | LEE H.
Flow
NO | Task | Test data | Expected result | Person in charge | Result |  | Pass/Fail |  |  | Remark
[7 empty] | 1st | 2nd | 3rd
1 | [Receiving an event message from OVMC] 1. Menu: Bus > Event/event > Device event 2. Input inquiry condition. 3. Click 'Search' button. | Test Data: A | 1. Show device list that meets the inquiry condition. | LEE. H | 1st
2nd
3rd
2 | [Sending a file of device event to AMC] 1. Menu: Bus > Scheduler > History Of Sub Job Execution 2. Input inquiry condition. 3. Click 'Search' button. 4. Location: 'D:/AFCDATA/DEPOTMC/UPLOAD-BACKUP' | Test Data: B | 1. The batch job executes after receiving data. 2. File Name: Linking Item(5).System ID(9).Creation Date(14).Sequence(5).dat | LEE. H | 1st |  |  |  |  | Batch jobs execute every 5 minutes.
2nd
3rd
2. Test Data
NO | Item | Value
A | Device ID
B | Main Job | [BD001] Jobs for Device Information
| Sub Job | [BD00103] Send Device Event
| Linking Item | FB703(Bus) / FT703(Tram)
Receiving an status event message
from OVMC
Sending a file of device event
to AMC

## 003
▶ Test Case SIT-OVM-DUM-04-003 : Receiving device status information / sending from AMC to OASA MC
1. Test Scenario
Test date |  | 1st |  | Tester |  | 1st
|  | 2nd |  |  |  | 2nd
|  | 3rd |  |  |  | 3rd
Description |  | Receiving device status information / sending from AMC to OASA MC |  |  |  |  | Written by
Flow
NO | Task | Test data | Expected result | Person in charge | Result |  | Pass/Fail |  |  | Remark
[7 empty] | 1st | 2nd | 3rd
1 | [Received Status Information from SMC] 1. Received Device Status Information Message from METRO-SMC 2. Check at Operation > Monitoring > Device Communication | Test Data : A | 1. Device Communication information is Inquired | ROH S.W. | 1st
2nd
3rd
2 | [Create and send Status Information file] 1. Execute smartafc.rail.devicecontrol.devicelastconn.job.CreateAndSendBusDeviceLastConnJob 2. -Main Job : AD003 -Sub Job: AD00303 | Test Data : B | 1.Status information file is created under: AFCDATA/STASYMC/UPLOAD/ -FB708.createSystemId(9).creatdate(14).sequence(5).dat | ROH S.W. | 1st
2nd
3rd
2. Test Data
NO | Item | Value
A | Device Class Name | OVMC
| Device ID | 220000001
| Last Communication Time Range | 6Hour
B | Linking Item ID | FB708(BUS) FT708(TRAM)
| Cycle | Every 5 min
Received Status Info from SMC
Create and send Status Info file

## 004
▶ Test Case SIT-OVM-DUM-04-004 : Receiving device status information at OASA MC
1. Test Scenario
Test date |  | 1st |  | Tester |  | 1st
|  | 2nd |  |  |  | 2nd
|  | 3rd |  |  |  | 3rd
Description |  | Receiving device status information at OASA MC |  |  |  |  | Written by
Flow
NO | Task | Test data | Expected result | Person in charge | Result |  | Pass/Fail |  |  | Remark
[7 empty] | 1st | 2nd | 3rd
1 | [Received status information from AMC] 1.Main Job : [AD004] ExecuteRcvFileDelegJob sub job : AD00401 Execution - smartafc.operation.batch.rcv.job.ExecuteRcvFileDelegJob | Test Data : A | 1. File is moved from /data001/AFCDATA/OASAMC/SHARERCV/ to ./data001/AFCDATA/OASAMC/SHARERCV-BACKUP/ | ROH S.W. | 1st
2nd
3rd
2 | [Received status information from AMC] 1. Inquire test data. 2. Click 'Search' button. 3. Show data that meets the inquiry condition | Test Data : B | history Of Sub Job Execution data is inquired Execution Result: [02] Job Success | ROH S.W. | 1st
2nd
3rd
3 | [Inquiry of status Info] 1. Check at Operation > Monitoring > Device Communication 2. Inquire test data. 3. Click 'Search' button. | Test Data : C | Device Communication data received from SMC is inquired. | ROH S.W. | 1st
2nd
3rd
2. Test Data
NO | Item | Value
A | Linking Item ID | FB708(BUS) FT708(TRAM)
B | System Class | Operation
| Main Job | AD004
| Sub Job | AD00401
| Execution Date | Current date
C | Agency Name | OSY
| Device Class Name | OVMC
| Device ID | 220000001
| Last Communication Time Range | 6Hour
Received Status information from AMC
Inquiry of Status information